## SRWMD BMAP 2020
ProjID | BMAP project ID | BMAPID | Lead Entity | Partners | Project Number | Project Name | Project Description | Project Type | Project Status | Estimated Start Date | Estimated Completion Date | TN Reduction (lbs/yr) | TP Reduction (lbs/yr) | Location | Acres Treated | Cost Estimate | Cost Annual O&M | Funding Source | Funding Amount | DEP Contract Agreement Number | WMD Contract Agreement Number | Latitude | Longitude | BMAP status
86 | 2118 | SAFE | Alachua County | SRWMD | AC-01 | Poe Springs Domestic Sewage Infrastructure Upgrade | Install new waterless restrooms with larger holding tanks adjacent to springshed. Replace OSTDS with enhanced passive nitrogen system using biosorption activated media (BAM). Reduction estimate to land surface of 5,776 lb-N/yr. | Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Completed | 2018 | 2020 | 225 | N/A | Alachua County | N/A | 346600 | Not provided | County/ SRWMD | County - $196,600/ SRWMD - $150,000 | N/A | Not provided | Not provided | Not provided | Adopted
46 | 2117 | SAFE | Alachua County | DEP | AC-02 | Hornsby Spring Restoration | Install temporary aerator to improve dissolved oxygen conditions, remove sediment to improve spring flow, and install submerged aquatic vegetation to improve water quality. Reduction estimate to land of 1,260 lb-N/yr. | Hydrologic Restoration | Underway | 2017 | 2021 | 340.2 | N/A | Alachua County | TBD | 443480 | N/A | County/ DEP | County - $20,000/ DEP - $423,480 | TBD | Not provided | Not provided | Not provided | Adopted
173 | 2116 | SAFE | Alachua County | DEP | AC-03 | Mill Creek Sink Water Quality Improvement Project - Phase II | See AL-01 for the Phase I project info. Phase II is the acquisition of 240 additional acres surrounding and upstream of Mill Creek Swallet. | Land Acquisition | Canceled | 2017 | 2018 | N/A | N/A | Alachua County | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Adopted
| 2115 | SAFE | Alachua County | DEP/ Gainesville Clean Water Partnership | AC-04 | Fertilizer Social Marketing Campaign | Implement a social marketing campaign designed to reduce fertilizer use and to estimate the resultant load reduction. | Education Efforts | Underway | 2018 | 2021 | TBD | N/A | Alachua County | N/A | 435000 | N/A | Partnership/ DEP | Partnership - $300,000/ DEP - $135,000 | NF033 | Not provided | Not provided | Not provided | Adopted
| 2114 | SAFE | Alachua County | Adventure Outpost | AC-05 | Interactive Paddling Trips | Implement education by coordinating 5-6 interactive paddling trips on the Santa Fe River with 120 stakeholders to explore actions that affect the health of our springs and groundwater. | Education Efforts | Completed | 2018 | 2019 | N/A | N/A | Alachua County | N/A | 12600 | N/A | County/ Wildlife Foundation of Florida Springs Protection License Plate Grant | County - $6,900/ Wildlife Foundation of Florida Springs Protection License Plate Grant - $5,700 | N/A | Not provided | Not provided | Not provided | Adopted
| 2119 | SAFE | Alachua County | Gainesville Clean Water Partnership | AC-06 | Interactive Stormwater and Wastewater Model | Interactive table top model for teaching children and adults about the difference between storm sewers and sanitary sewers. | Education Efforts | Completed | 2017 | 2018 | N/A | N/A | Alachua County | N/A | 6500 | N/A | Partnership | $6,500 | N/A | Not provided | Not provided | Not provided | Adopted
| 2120 | SAFE | Alachua County | N/A | AC-07 | Santa Fe River Springs Submerged Aquatic Vegetation (SAV) Assessment | The goal of this project is to document the current condition of SAV at selected springs (pools and associated spring runs) on the Santa Fe River. | Study | Underway | 2017 | 2022 | N/A | N/A | Alachua County | N/A | 24500 | N/A | County/ Wildlife Foundation of Florida Springs Protection License Plate Grant | $40,000 | N/A | Not provided | Not provided | Not provided | Adopted
| 2121 | SAFE | Alachua County | Gainesville Clean Water Partnership | AC-08 | Stream Bioassessment Study | The Stream Bioassessment Study project includes Stream Condition Index (SCI) in-stream biological assessment and Hester-Dendy sampling and analysis to provide ambient monitoring for TMDL and impaired watersheds. | Monitoring/Data Collection | Completed | 2017 | 2019 | N/A | N/A | Alachua County | N/A | 85969.84 | N/A | FDOT | $85,970 | N/A | Not provided | Not provided | Not provided | Adopted
46 | 2122 | SAFE | Alachua County | Camp Kulaqua | AC-09 | Hornsby Springs Dissolved Oxygen and Faunal Study | This project seeks to evaluate the role of dissolved oxygen temporally and spatially and to explore what effect this may have on organisms, particularly macro-invertebrates. | Study | Completed | 2018 | 2019 | N/A | N/A | Alachua County | N/A | 14000 | N/A | County/ Wildlife Foundation of Florida Springs Protection License Plate Grant | $14,000 | N/A | Not provided | Not provided | Not provided | Adopted
| 2123 | SAFE | Alachua County | Local and State Parks | AC-10 | Santa Fe River Springs Signage | The goal of this project is to increase awareness about the springs of the Santa Fe River and current springs issues and solutions. Interpretive signs will be installed at selected springs or parks along the Santa Fe River. | Education Efforts | Completed | 2018 | 2019 | N/A | N/A | Alachua County | N/A | 12600 | N/A | County/ Wildlife Foundation of Florida Springs Protection License Plate Grant | $12,600 | N/A | Not provided | Not provided | Not provided | Adopted
| 4553 | SAFE | Alachua County | Wildlife Foundation of Florida/ Gainesville Clean | AC-11 | Aquifer Model | Mobile model used for outreach to children and adults designed and created to teach the public about the connection between how what we do on the land surface and how we use water affects our springs, rivers, and aquifer. | Education Efforts | Ongoing | 2018 | N/A | N/A | N/A | Alachua County | N/A | 6000 | Not provided | County/ Fish & Wildlife Foundation of Florida Springs Protection License Plate Grant | Not provided | N/A | Not provided | Not provided | Not provided | Adopted
274 | 4554 | SAFE | Alachua County | N/A | AC-12 | Poe Spring Sediment Removal and Habitat Restoration | Alachua County proposes to remove 1,100 to 1,200 cubic yards of sediment from the main spring and stabilize soils and restore habitat. | Muck Removal/Restoration Dredging | Planned | 2023 | TBD | N/A | N/A | Santa Fe River Basin - Alachua County | N/A | 259970 | N/A | SRWMD/ DEP | N/A | N/A | Not provided | Not provided | Not provided | Adopted
| 4555 | SAFE | Alachua County | City of Gainesville | AC-13 | 4 Creeks Preserve Acquisition | Fee simple acquisition. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. | Land Acquisition | Completed | 2018 | 2018 | N/A | N/A | Santa Fe River Basin - Alachua County | 716 | 4382966 | N/A | Wild Spaces and Public Places II Surtax | Not provided | N/A | Not provided | Not provided | Not provided | Adopted
| 4556 | SAFE | Alachua County | N/A | AC-14 | Poe Springs Aquatic Habitat Enhancement and Outreach | The project goal is enhancement of the aquatic plant community and assessment of infaunal macroinvertebrate populations in selected areas of Poe and Little Poe springs. | Wetland Restoration | Completed | 2018 | 2020 | N/A | N/A | Poe Springs Alachua County | N/A | 12500 | N/A | County/ Fish & Wildlife Foundation of Florida Springs Protection License Plate Grant | $12,500 | N/A | Not provided | Not provided | Not provided | Adopted
| 4557 | SAFE | Alachua County | N/A | AC-15 | Santa Fe River - Santa Fe River Ranch (Hitchcock) | Conservation easement acquisition. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. Drains into Santa Fe River. | Land Acquisition | Underway | 2018 | 2022 | N/A | N/A | Santa Fe River Basin - Alachua County | 2168 | N/A | N/A | Wild Spaces and Public Places II Surtax | N/A | N/A | Not provided | Not provided | Not provided | Adopted
| 4558 | SAFE | Alachua County | N/A | AC-16 | Hickory Sink - Kanapaha Timber Land & Cattle (Lee) | Conservation easement acquisition. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. | Land Acquisition | Planned | 2018 | Not provided | N/A | N/A | Santa Fe River Basin - Alachua County | 3948 | N/A | N/A | Wild Spaces and Public Places II Surtax | N/A | N/A | Not provided | Not provided | Not provided | Adopted
| 4559 | SAFE | Alachua County | City of Gainesville/ FDOT District 2 | AC-17 | Pet Waste Outreach | Implement social marketing campaign to motivate citizens to scoop, bag, and trash dog wastes at home and in the community. Reduces bacteria and nutrient sources in all watersheds. | Enhanced Public Education | Ongoing | 2018 | N/A | N/A | N/A | Alachua County | N/A | 40655 | 7000 | Alachua County/ City of Gainesville/ FDOT District 2/ SJRWMD | Not provided | N/A | Not provided | Not provided | Not provided | Adopted
| 4560 | SAFE | Alachua County | City of Gainesville/ FDOT District 2 | AC-18 | Landscaping Debris Social Marketing | Implement social marketing campaign designed to get citizens to keep landscaping debris out of the roads and stormwater collection systems. Reduces bacteria and nutrient sources in all watersheds. | Enhanced Public Education | Ongoing | 2018 | N/A | N/A | N/A | Alachua County | N/A | 50000 | 7000 | Alachua County/ City of Gainesville/ FDOT District 2/ SJRWMD | Not provided | N/A | Not provided | Not provided | Not provided | Adopted
| 4561 | SAFE | Alachua County | City of Gainesville/ FDOT District 2 | AC-19 | Water Conservation and LID | Conduct targeted public outreach to encourage water conservation and rain harvesting. Includes rain barrel sales and LID promotion. | Enhanced Public Education | Ongoing | 2018 | N/A | N/A | N/A | Alachua County | N/A | N/A | Not provided | Alachua County/ City of Gainesville/ FDOT District 2/ SJRWMD | Not provided | N/A | Not provided | Not provided | Not provided | Adopted
| 4562 | SAFE | Alachua County | City of Gainesville/ FDOT District 2/ SJRWMD | AC-20 | Landscaping Behavior Change Social Marketing | Implement social marketing campaign designed to get citizens to make landscaping behavior changes that reduce nutrients in stormwater. Reduces nutrients sources in all watersheds. | Enhanced Public Education | Completed | 2018 | 2019 | Not provided | N/A | Alachua County | N/A | 600000 | N/A | Alachua County/ City of Gainesville/ FDOT District 2/ SJRWMD | Not provided | N/A | Not provided | Not provided | Not provided | Adopted
| 4563 | SAFE | Alachua County | City of Gainesville/ FDOT District 2 | AC-21 | Alachua County Water Quality Code Implementation | Alachua County Water Quality Code Implementation, includes public education, outreach, and enforcement. | Regulations, Ordinances, and Guidelines | Completed | 2018 | 2019 | N/A | N/A | Alachua County | N/A | 17400 | N/A | Alachua County/ City of Gainesville/ FDOT District 2/ SJRWMD | Not provided | N/A | Not provided | Not provided | Not provided | Adopted
| 4564 | SAFE | Alachua County | N/A | AC-22 | Fertilizer and Landscape Irrigation Codes | Adopt and enforce Fertilizer Management and Landscape Irrigation Ordinances. Reduce volume of runoff from over irrigation and reduce nutrient loading from the use of fertilizers. | Regulations, Ordinances, and Guidelines | Completed | 2018 | 2019 | N/A | N/A | Alachua County | N/A | N/A | Not provided | Alachua County General Fund | Not provided | N/A | Not provided | Not provided | Not provided | Adopted
| 5461 | SAFE | Alachua County | N/A | AC-23 | Countywide Stormwater Treatment Code | Adopt a stormwater treatment code for new development. Code requires 70/80% TN/TP reductions in stormwater discharges. 95% for OFWs and 10% below predevelopment for impaired waters. LID techniques are required in sensitive karst area. | Regulations, Ordinances, and Guidelines | Completed | N/A | 2019 | N/A | N/A | Alachua County | N/A | N/A | Not provided | Alachua County Stormwater Assessment | Not provided | N/A | Not provided | Not provided | Not provided | Adopted
| 5462 | SAFE | Alachua County | N/A | AC-24 | Countywide Florida Friendly Landscaping Homeowner Association Code | Adopt a FFL HOA Code that prohibits HOAs from prohibiting FFL. The code also prohibits neighborhood codes, covenants, and regulations adopted after 2016 from requiring irrigation. | Regulations, Ordinances, and Guidelines | Completed | N/A | 2019 | N/A | N/A | Alachua County | N/A | N/A | Not provided | Alachua County General Fund | Not provided | N/A | Not provided | Not provided | Not provided | Adopted
| 5463 | SAFE | Alachua County | N/A | AC-25 | Aquifer Awareness Campaign | Billboards and social media to teach the public about the connection between our water use, the aquifer, and the health of our springs. | Enhanced Public Education | Ongoing | Not provided | N/A | N/A | N/A | Alachua County | N/A | 20000 | 10000 | Alachua County General Fund/ Alachua County/ City of Gainesville/ FDOT District 2/ SJRWMD/ Fish & Wildlife Foundation of Florida Springs Protection License Plate Grant | $10,000 | N/A | Not provided | Not provided | Not provided | Adopted
| 5464 | SAFE | Alachua County | N/A | AC-26 | J Kinnard | Fee simple acquisition. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. | Land Acquisition | Completed | N/A | 2019 | N/A | N/A | Santa Fe River Basin - Alachua County | 49.3 | 221850 | N/A | Wild Spaces Public Place II Surtax | Wild Spaces and Public Places Sales Tax - $221,850 | N/A | Not provided | Not provided | Not provided | Adopted
| 5465 | SAFE | Alachua County | N/A | AC-27 | R&D Kinnard | Fee simple acquisition. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. | Land Acquisition | Completed | N/A | 2019 | N/A | N/A | Santa Fe River Basin - Alachua County | 15 | 67500 | N/A | Wild Spaces Public Place II Surtax | Wild Spaces and Public Places Sales Tax - $67,500 | N/A | Not provided | Not provided | Not provided | Adopted
| 5466 | SAFE | Alachua County | N/A | AC-28 | Lundgren | Donation from land owner. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. Drains into Santa Fe River. | Land Acquisition | Underway | N/A | 2021 | N/A | N/A | Santa Fe River Basin - Alachua County | 234 | 0 | N/A | Donation | Donation - $0 | N/A | Not provided | Not provided | Not provided | Adopted
| 5467 | SAFE | Alachua County | N/A | AC-29 | Brown | Conservation easement acquisition. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. | Land Acquisition | Underway | N/A | 2022 | N/A | N/A | Santa Fe River Basin - Alachua County | 371 | 556500 | N/A | Wild Spaces Public Place II Surtax | Not provided | N/A | Not provided | Not provided | Not provided | Adopted
| 5468 | SAFE | Alachua County | N/A | AC-30 | Mattews | Conservation easement acquisition. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. Drains into Santa Fe River. | Land Acquisition | Underway | N/A | 2021 | N/A | N/A | Santa Fe River Basin - Alachua County | 247 | 370500 | N/A | Wild Spaces Public Place II Surtax | Not provided | N/A | Not provided | Not provided | Not provided | Adopted
| 5469 | SAFE | Alachua County | N/A | AC-31 | Johnson | Fee Simple Land Conservation acquisition. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. Drains into Lake Santa Fe. | Land Acquisition | Completed | N/A | 2020 | N/A | N/A | Santa Fe River Basin - Alachua County | 243.67 | 1924993 | N/A | Wild Spaces Public Place II Surtax | Wild Spaces and Public Places Sales Tax - $2,265,246 | N/A | Not provided | Not provided | Not provided | Adopted
| 5783 | SAFE | ACEPD | N/A | AC-32 | Springs Protection Videos | Five to six 30-second videos on various aspects of springs protection for social media and paid media outlets. | Education Efforts | Ongoing | 2021 | N/A | N/A | N/A | Alachua County | N/A | 17000 | N/A | County/ Wildlife Foundation of Florida Springs Protection License Plate Grant | $12,000 | N/A | N/A | Not provided | Not provided | Adopted
303 | 5784 | SAFE | ACEPD | City of Gainesville/ FDOT District 2/ SRWMD/SJRWMD | AC-33 | Turf Swap | Rebates to property owners that convert irrigated turf to FFL or implement water saving irrigation retrofits. | Education Efforts | Ongoing | 2016 | N/A | N/A | N/A | Alachua County | N/A | 1000000 | N/A | SRWMD/ SJRWMD | SRWMD -$150,000/ SJRWMD - $300,000 | WS003 | SJRWMD 28913/ SRWMD 1920-190 | Not provided | Not provided | Adopted
| 5785 | SAFE | Alachua County | UF | AC-34 | Quantifying Nitrogen Leaching from Residential Soils in Alachua County Phase 1 | Assess nitrogen leaching from actual landscapes in Alachua County. A variety of lawn ages and soil types will be assessed along with mulched planting beds. Soil cores will be analyzed and will be collected from 11 lysimeters installed in yards. | Study | Completed | 2019 | 2020 | N/A | N/A | Santa Fe River Basin - Alachua County | N/A | 32405 | N/A | Alachua County Stormwater Assessment | $32,425 | N/A | Not provided | Not provided | Not provided | Adopted
| 5786 | SAFE | Alachua County | UF | AC-35 | Quantifying Nitrogen Leaching from Residential Soils in Alachua County Phase 2 | This phase will investigate nitrogen leaching in yards undergoing a variety of treatments, including mineral fertilizer, a biosolids based fertilizer, and top dressing with compost. New lysimeters will be installed in a natural area for comparison. | Study | Planned | 2021 | 2022 | N/A | N/A | Santa Fe River Basin - Alachua County | N/A | 43794 | N/A | Alachua County Stormwater Assessment | $43,794 | N/A | Not provided | Not provided | Not provided | Adopted
| 5787 | SAFE | Alachua County | N/A | AC-36 | An Evaluation of Nutrient Sources and Potential Nutrient Reduction Projects for Poe Spring | Initial literature and data review phase of a project to identify nutrient sources in Poe Springs and potential nutrient reduction projects for the spring and groundwater generally. | Study | Planned | 2021 | 2021 | N/A | N/A | Santa Fe River Basin - Alachua County | N/A | 34085 | N/A | Alachua County Stormwater Assessment | $34,085 | N/A | Not provided | Not provided | Not provided | Adopted
| 5788 | SAFE | Alachua County | N/A | AC-37 | An Evaluation of Nutrient Sources and Potential Nutrient Reduction Projects for Lake Santa Fe | Initial literature and data review phase of a project to identify nutrient sources in Lake Santa Fe and potential nutrient reduction projects for the lake. | Study | Planned | 2021 | 2021 | N/A | N/A | Santa Fe River Basin - Alachua County | N/A | 34085 | N/A | Alachua County Stormwater Assessment | $34,085 | N/A | Not provided | Not provided | Not provided | Adopted
| 5789 | SAFE | Alachua County | N/A | AC-38 | Warny | Donation from land owner. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. | Land Acquisition | Underway | 2020 | 2021 | N/A | N/A | Santa Fe River Basin - Alachua County | 80 | 0 | N/A | Donation | Donation - $0 | N/A | Not provided | Not provided | Not provided | Adopted
| 5790 | SAFE | Alachua County | N/A | AC-39 | Pinkoson & Upshaw | Fee simple land conservation acquisition. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. | Land Acquisition | Underway | 2020 | 2022 | N/A | N/A | Santa Fe River Basin - Alachua County | 119.3 | N/A | N/A | Wild Spaces Public Place II Surtax | N/A | N/A | Not provided | Not provided | Not provided | Adopted
| 5791 | SAFE | Alachua County | N/A | AC-40 | Bryson | Land conservation easement acquisition. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. Drains into Little Lake Santa Fe. | Land Acquisition | Planned | 2020 | 2023 | N/A | N/A | Santa Fe River Basin - Alachua County | 80 | N/A | N/A | Wild Spaces Public Place II Surtax | N/A | N/A | Not provided | Not provided | Not provided | Adopted
| 5792 | SAFE | Alachua County | N/A | AC-41 | Santa Fe River - Santa Fe River Ranch (Hitchcock II) | Conservation easement acquisition. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. | Land Acquisition | Planned | 2020 | 2023 | N/A | N/A | Santa Fe River Basin - Alachua County | 205 | N/A | N/A | Wild Spaces and Public Places II Surtax | N/A | N/A | Not provided | Not provided | Not provided | Adopted
| 5793 | SAFE | Alachua County | N/A | AC-42 | Waldo Tree Farm | Fee simple land conservation acquisition. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. | Land Acquisition | Planned | 2020 | 2022 | N/A | N/A | Santa Fe River Basin - Alachua County | 198 | N/A | N/A | Wild Spaces Public Place II Surtax | N/A | N/A | Not provided | Not provided | Not provided | Adopted
2087 | 5794 | SAFE | Alachua County | SRWMD | AC-43 | Rembert | Conservation easement acquisition. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. Drains into Mill Creek Sink. | Land Acquisition | Planned | 2020 | 2024 | N/A | N/A | Santa Fe River Basin - Alachua County | 718 | 2000000 | N/A | Wild Spaces and Public Places II Surtax | N/A | N/A | Not provided | Not provided | Not provided | Adopted
| 5795 | SAFE | Alachua County | N/A | AC-44 | General Land Acquisition | Fee simple & conservation easement acquisition. No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation. | Land Acquisition | Planned | 2020 | 2026 | N/A | N/A | Santa Fe River Basin - Alachua County | N/A | N/A | N/A | Wild Spaces and Public Places II Surtax | N/A | N/A | Not provided | Not provided | Not provided | Adopted
80 | 2129 | SAFE | City of Alachua | DEP/ SRWMD | AL-01 | Mill Creek Sink Water Quality Improvement Project | Purchase property to install water quality BMPs to reduce pollutant loads discharging directly into the sink. Nutrient loading should be reduced by 66 % and benefit Hornsby Spring. | BMP Treatment Train | Underway | 2017 | 2021 | TBD | N/A | Alachua County | Not provided | 1400000 | Not provided | DEP/ SRWMD | DEP - $1,000,000/ SRWMD - $400,000 | LP6103L | Not provided | Not provided | Not provided | Adopted
54 | 2130 | SAFE | City of Archer | SRWMD | AR-01 | Holly Hills Stormwater Improvements | Increase storage within existing stormwater ponds to alleviate flooding and improve water quality. | Stormwater System Upgrade | Underway | 2017 | 2019 | Not provided | N/A | Alachua County | Not provided | 87000 | Not provided | City/ SRWMD | City - $4,000/ SRWMD - $83,000 | N/A | Not provided | Not provided | Not provided | Adopted
238 | 5796 | SAFE | City of Archer | SRWMD/ DEP/ USDA/ DEO | AR-02 | City of Archer Wastewater Systems Improvements | Design and construction of a wastewater collection system, lift stations, and treatment plant to phase out the use of septic tanks in the City of Archer. | Wastewater Service Area Expansion | Planned | 2021 | 2023 | TBD | N/A | Alachua County | Not provided | 9678579 | 212405 | TBD | TBD | N/A | TBD | 29.53 | -82.52 | Adopted
91 | 2137 | SAFE | Columbia County | SRWMD | CC-01 | Rum Island Park | Install new public restrooms with lift station and septic system in place of portable toilets. Install BAM to reduce nutrients around septic system. Project also involves bank restoration and dredging. | Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Completed | 2018 | 2019 | Not provided | N/A | Columbia County | N/A | 300000 | N/A | County/ SRWMD | County - $150,000/ SRWMD - $150,000 | N/A | Not provided | Not provided | Not provided | Adopted
134 | 2125 | SAFE | Columbia County | DEP | CC-02 | Ichetucknee Trace - Clay Hole Creek/ Alligator Lake Aquifer Recharge and Stormwater Mitigation | Construct swales, canals, and stormwater canal structures to direct water to Alligator Lake to provide erosion control and water quality treatment before water enters aquifer. Reduction estimate of load to land surface of 30,000 lb-N/yr. | Regional Stormwater Treatment | Underway | 2016 | 2020 | 8100 | N/A | Columbia County | Not provided | 2560000 | Not provided | County/ DEP | County - $300,000/ DEP - $2,260,000 | LP6103A | Not provided | Not provided | Not provided | Adopted
133 | 2106 | SAFE | Columbia County | DEP | CC-03 | Ichetucknee Trace - Cannon Creek Project | Provide flood mitigation, water quality improvement, and aquifer recharge through the replacement of an old drainage well and 13 acres of wetland construction. Reduction estimate of load to land surface of 10,000 lb-N/yr. | Regional Stormwater Treatment | Planned | TBD | 2021 | 2700 | N/A | Columbia County | 13 | 3030000 | Not provided | County/ DEP | County - $780,000/ DEP - $2,250,000 | S0924 | Not provided | Not provided | Not provided | Adopted
35 | 2127 | SAFE | Columbia County | DEP | CC-04 | Dream Inn Motel WWTP Closure | Remove the noncompliant WWTP that serves the motel and connect to the county's sewer system. This also includes relocating, upgrading, and enlarging the county WWTF to handle flow. Estimated load reduction to land surface of 1,000 lb-N/yr. | WWTF Upgrade | Completed | 2017 | 2018 | 360 | N/A | Columbia County | N/A | 354737 | N/A | County/ SRWMD | County - $210,437/ SRWMD - $144,300 | N/A | Not provided | Not provided | Not provided | Adopted
| 2093 | SAFE | FDACS | Agricultural Producers | FDACS-01 | BMP Implementation and Verification - Farm Fertilizer | EnroF2:F12llment and verification of farm fertilizer BMPs by agricultural producers. Acres Treated based on FDACS December 2019 NOI Enrollment and FSAID VI. Reductions based on efficiencies referenced in the BMAP and 100% NOI Enrollment. | Agricultural BMPs | Underway | Not provided | N/A | 232273.3386 | N/A | Basinwide | 41973 | N/A | N/A | TBD | TBD | N/A | Not provided | Not provided | Not provided | Adopted
| 5800 | SAFE | FDACS | Agricultural Producers | FDACS-01a | BMP Implementation and Verification - Farm Fertilizer | Enrollment and verification of farm fertilizer BMPs by agricultural producers. Acres Treated and reductions based on FDACS December 2020 NOI Enrollment and FSAID VII. | Agricultural BMPs | Completed | Not provided | 2020 | 125020 | N/A | Basinwide | 63046 | TBD | TBD | Not provided | Not provided | N/A | N/A | Not provided | Not provided | Adopted
| 2091 | SAFE | FDACS | Agricultural Producers | FDACS-02 | BMP Implementation and Verification - Livestock Waste | Enrollment and verification of livestock waste BMPs by agricultural producers. Reductions based on efficiencies referenced in the BMAP and 100% NOI enrollment of unenrolled acres. | Agricultural BMPs | Underway | Not provided | N/A | 51541.1959 | N/A | Basinwide | 45705 | N/A | N/A | TBD | TBD | N/A | Not provided | Not provided | Not provided | Adopted
| 5801 | SAFE | FDACS | Agricultural Producers | FDACS-02a | BMP Implementation and Verification - Livestock Waste | Enrollment and verification of livestock waste BMPs by agricultural producers. Acres Treated based on FDACS December 2020 NOI Enrollment and FSAID VII. | Agricultural BMPs | Completed | Not provided | 2020 | 24844 | N/A | Basinwide | 76679 | TBD | TBD | Not provided | Not provided | N/A | N/A | Not provided | Not provided | Adopted
| 2095 | SAFE | FDOT District 2 | Not provided | FDOT-01 | Fertilizer Elimination | Eliminate fertilizer use in rights-of way. Reduction estimate of load to land surface of 16,901 lb-N/yr. | Fertilizer Cessation | Completed | Not provided | 2010 | 4563.27 | N/A | Basinwide | 776 | Not provided | Not provided | Not provided | Not provided | Not provided | Not provided | 29.929355 | -82.423323 | Adopted
| 2141 | SAFE | DEP FPS | N/A | FPS-01 | Ichetucknee Springs State Park | Remove septic system in wetlands at the Dampier's Landing Bath House and connect to existing wastewater treatment system in the uplands. | OSTDS Phase Out | Planned | TBD | TBD | Not provided | N/A | Columbia County | TBD | Not provided | N/A | DEP | Not provided | N/A | Not provided | Not provided | Not provided | Adopted
93 | 2124 | SAFE | Gilchrist County | SRWMD | GC-01 | Santa Fe Park and Boat Ramp | Replace boat ramp, add docks and canoe launch, and remedy drainage to reduce sediment and nutrients. | Regional Stormwater Treatment | Completed | 2018 | 2019 | Not provided | N/A | Gilchrist County | Not provided | 129800 | Not provided | County/ SRWMD | County - $6,800/ SRWMD - $123,000 | N/A | Not provided | Not provided | Not provided | Adopted
| 2109 | SAFE | Management Strategies | TBD | GOLF-01 | Golf Course Reduction Credits | 6 % BMP credit on golf course load to groundwater, assuming 100 % BMP implementation by golf course owners. | Golf Course or Sports Field BMPs | Planned | TBD | TBD | 2115.3866 | N/A | Basinwide | TBD | TBD | N/A | TBD | TBD | TBD | Not provided | N/A | N/A | Adopted
73 | 2113 | SAFE | GRU | DEP | GRU-01 | Wetland Creation at Shands Facility | Constructed a recharge wetland at a new Shands facility that removes nutrients from reclaimed water and stormwater and provides aquifer recharge. | Constructed Wetland Treatment | Canceled | N/A | N/A | N/A | N/A | Alachua County | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Adopted
197 | 2098 | SAFE | GRU | SRWMD | GRU-02 | Oakmont Reclaimed Water Main Extension | Provide reclaimed water to irrigate 136 residential properties and 3 acres of common area. | WWTF Diversion to Reuse | Canceled | N/A | N/A | N/A | N/A | Alachua County | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Adopted
83 | 2099 | SAFE | GRU | SRWMD | GRU-03 | Oakmont Recharge Wetland | Construct a recharge wetland in an existing stormwater retention basin that will reduce nutrients while recharging aquifer. Canceled in 2019. Scope has changed - GRU looking into feasibility of new project for a large constructed infiltrating wetland. | Constructed Wetland Treatment | Canceled | N/A | N/A | N/A | N/A | Alachua County | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Adopted
| 2131 | SAFE | City of Hampton | USACE | HA-01 | Master Drainage Study | Undertake study to address severe flooding issues. | Study | Planned | TBD | 2020 | N/A | N/A | Bradford County | N/A | 150000 | N/A | USACE | $150,000 | N/A | Not provided | 29.865457404598946 | -82.13558586930948 | Adopted
59 | 2132 | SAFE | City of High Springs | DEP/ SRWMD | HS-01 | Infiltrative Wetlands for WWTF Effluent Treatment/ Disposal - Phase I | Convert City's existing effluent sprayfield into infiltration wetlands; 10 of 20 acres will be constructed in Phase I. This will benefit water quality in Hornsby and Poe Springs. Reduction estimated load to land surface of 4,870 lb-N/yr. | Constructed Wetland Treatment | Underway | 2018 | 2019 | 1753.2 | N/A | Alachua County | 10 | 1708500 | Not provided | DEP | $1,708,500 | LP61037 | Not provided | 29.79717 | -82.6213744 | Adopted
50 | 2133 | SAFE | City of High Springs | DEP/ SRWMD | HS-02 | Wastewater Collection System Extension - Phase A1 | Provide central sewer to remaining areas served by septic systems. Elimination of 132 septic systems. Reduction estimate to land surface of 2,640 lb-N/yr. | OSTDS Phase Out | Completed | 2016 | 2019 | 1188 | N/A | Alachua County | N/A | 3432700 | 5000 | City/ DEP | City - $125,000/ DEP - $3,307,700 | LP61037 | Not provided | Not provided | Not provided | Adopted
55 | 2134 | SAFE | City of High Springs | DEP/ SRWMD | HS-03 | Camp Kulaqua-Hornsby Spring Water Quality Improvement Project | Remove onsite wastewater treatment plant and effluent disposal and install new wastewater line to city WWTP. Reduction estimated load to land surface of 97 lb-N/yr. | WWTF Upgrade | Completed | 2015 | 2018 | 43.65 | N/A | Alachua County | N/A | 500000 | Not provided | DEP/ SRWMD | DEP - $450,000/ SRWMD - $50,000 | S0889 | Not provided | 29.850405 | -82.591614 | Adopted
49 | 2135 | SAFE | City of High Springs | SRWMD | HS-04 | Septic Tank Abatement | Eliminate 13 residential septic systems and connect to City's central sewer system. Reduction estimate to land surface of 330 lb-N/yr. | OSTDS Phase Out | Completed | 2017 | 2018 | 148.5 | N/A | Alachua County | N/A | 175000 | N/A | City/ SRWMD | City - $25,000/ SRWMD - $150,000 | N/A | Not provided | Not provided | Not provided | Adopted
298 | 2136 | SAFE | City of High Springs | TBD | HS-05 | Wastewater Collection System Extension - Phase A2 | Provide central sewer to remaining areas served by septic systems. Elimination of 168 septic systems. Reduction estimate revised in 2018 to reflect estimate NSILT estimate of load to groundwater from Santa Fe OSTDS for 168 OSTDS removed. | OSTDS Phase Out | Underway | TBD | 2021 | 1582 | N/A | Alachua County | N/A | 3562000 | 5000 | DEP/ SRWMD | TBD | N/A | Not provided | 29.8143 | -82.59768 | Adopted
297 | 2126 | SAFE | City of High Springs | TBD | HS-06 | WWTF Upgrade | WWTF upgrades to meet AWT standards. Effluent will be further treated with a constructed infiltrative/treatment wetland. | WWTF Upgrade | Underway | TBD | 2020 | TBD | N/A | Alachua County | 10 | 4960240 | 108000 | City/ SRWMD | TBD | N/A | Not provided | 29.7925 | -82.61222 | Adopted
57 | 2105 | SAFE | City of Lake City | DEP | LC-01 | I-75/ SR 47 Cannon Creek Sink Wastewater Improvement Project - Phase I | Eliminate septic systems from 30 businesses and 5 residences to benefit water quality in Ichetucknee Spring. Reduction estimate to land surface of 11,950 lb-N/yr. | OSTDS Phase Out | Underway | 2018 | 2021 | 5377.5 | N/A | Columbia County | N/A | 3400871 | 1000 | City/ DEP | City - $1,703,415/ DEP - $1,697,456 | LP12030 | Not provided | 30.1204 | -82.6627 | Adopted
58 | 2097 | SAFE | City of Lake City | DEP/ SRWMD/ Columbia County | LC-02 | Ichetucknee Springshed Water Quality Improvement Project | Convert effluent disposal system into 120 acres of constructed wetlands that provide 1.58 mgd of recharge water to aquifer and reduce nitrogen loads from WWTP by 85 %. Reduction estimated load to land surface of 77,000 lb-N/yr. | Constructed Wetland Treatment | Completed | 2014 | 2016 | 27720 | N/A | Columbia County | 120 | 5005175 | Not provided | City/ DEP/ SRWMD/ Columbia County | City - $200,000/ DEP - $3,900,000/ SRWMD - $805,175/ County - $100,000 | S0675 | Not provided | Not provided | Not provided | Adopted
2100 | 2096 | SAFE | City of Lake City | SRWMD | LC-03 | Reclaimed Water System Upgrade - Phase I | Upgrade existing system to allow reclaimed water to be used by local golf course and farmer. Noted as canceled in 2018 by SRWMD. | WWTF Diversion to Reuse | Planned | 2021 | 2022 | N/A | N/A | Columbia County | TBD | 1086340 | Not provided | City/ SRWMD | City - $86,340/ DEP - $1,000,000 | N/A | Not provided | 30.130065 | -82.680215 | Adopted
| 2128 | SAFE | Management Strategies | TBD | LG-01 | Public Education | Adopted fertilizer ordinance. | Education Efforts | Planned | TBD | TBD | 3469.9459 | N/A | Basinwide | TBD | TBD | N/A | TBD | TBD | TBD | Not provided | N/A | N/A | Adopted
88 | 2094 | SAFE | City of Newberry | SRWMD | NEW-01 | Potable Water and Central Wastewater Improvements | Replace existing water and wastewater lines in close proximity to historic district, thereby reducing unaccounted water loss and preventing potential sewage spills. | WWTF Upgrade | Completed | 2017 | 2018 | TBD | N/A | Alachua County | TBD | 65000 | Not provided | City/ SRWMD | City - $26,566/ SRWMD - $38,434 | N/A | Not provided | Not provided | Not provided | Adopted
1877 | 5470 | SAFE | City of Newberry | SRWMD | NEW-02 | Canterbury Fairgrounds Wastewater Extension Project | Extend central wastewater lines to Canterbury Fairgrounds site and decommission the existing OSTDS. | OSTDS Phase Out | Planned | Not provided | 2020 | 354 | N/A | Alachua County | TBD | 220600 | 2000 | City/ SRWMD | TBD | N/A | Not provided | 29.656875 | -82.586242 | Adopted
| 5471 | SAFE | City of Newberry | SRWMD | NEW-03 | Newberry Enhanced Wetland Treatment Project | Installation and operation of a constructed treatment wetland on a portion of the existing sprayfield to achieve AWT standards for TN at the Newberry WWTF. | WWTF Nutrient Reduction | Planned | Not provided | 2022 | TBD | N/A | Alachua County | TBD | 2800000 | TBD | City/ SRWMD | TBD | N/A | Not provided | 29.635042 | -82.61655 | Adopted
| 2138 | SAFE | Management Strategies | DEP | OSTDS-01 | Enhancement of Existing OSTDS - Voluntary | Upgrade, replacement, modification, addition of effective nitrogen reducing features, initial connection to a central sewer system, or other action to reduce nutrient loading, voluntarily taken by the owner of an OSTDS within the BMAP. | Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Underway | 2018 | N/A | TBD | N/A | Basinwide | N/A | TBD | N/A | DEP | TBD | TBD | Not provided | N/A | N/A | Adopted
| 2139 | SAFE | Management Strategies | DEP | OSTDS-02 | Enhancement of Existing OSTDS - Required | Upgrade, replacement, modification, addition of effective nitrogen reducing features, initial connection to a central sewer system, or other action taken to comply with the OSTDS Remediation Plan for the group of systems identified for remediation. | Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Planned | TBD | TBD | TBD | N/A | Basinwide | N/A | TBD | N/A | DEP | TBD | TBD | Not provided | N/A | N/A | Adopted
| 2140 | SAFE | Management Strategies | TBD | PD-01 | Dairy Reduction Credits | 15 % BMP credit on dairy load to groundwater assuming 100 % owner implemented BMPs on all dairy lands. | Agricultural BMPs | Planned | TBD | TBD | 7188.7475 | N/A | Basinwide | TBD | TBD | N/A | TBD | TBD | TBD | Not provided | N/A | N/A | Adopted
| 2110 | SAFE | Management Strategies | TBD | SF-01 | Sports Field Reduction Credits | 10 % BMP credit on sports field load to groundwater, assuming 100 % BMP implementation by sports field owners. | Golf Course or Sports Field BMPs | Planned | TBD | TBD | 151.6644 | N/A | Basinwide | TBD | TBD | N/A | TBD | TBD | TBD | Not provided | N/A | N/A | Adopted
106 | 2100 | SAFE | SRWMD | DEP/ Local Governments | SRWMD-01 | Suwannee River Surface Water Improvement Management (SWIM) Plan | Implementation and periodic review and update of the Suwannee River SWIM Plan which includes the Santa Fe River and Ichetucknee River. | Study | Completed | 2015 | 2017 | N/A | N/A | Basinwide | N/A | 238563 | N/A | NFWF/ SRWMD | NFWF - $138,563 | N/A | 15/16-052 | 29.9072 | -82.4723 | Adopted
7 | 2101 | SAFE | SRWMD | DEP/ Dairy Producers | SRWMD-02 | Improved Nutrient Application Practices in Dairy Operations - Phase 2 | To date, 9 agreements with dairies to install screen separators to reduce wastewater solids. 1 agreement with a dairy in the Santa Fe Basin. DEP has allocated $2,120,000 for districtwide program. Load reduction to land estimate of 1,485 lb-N/yr. | Agricultural BMPs | Underway | 2015 | TBD | 200.475 | N/A | Basinwide | N/A | 838245.29 | N/A | DEP | DEP - $2,120,000 | S0905 | 15/16-057 | 29.9072 | -82.4723 | Adopted
8 | 2102 | SAFE | SRWMD | DEP/ Dairy Producers | SRWMD-03 | Dairy Wastewater System Improvement | Cost-share projects with dairies to invest in advanced treatment technologies (bioreactors), additional wastewater storage, and advanced manure solid separation. Canceled because project location was determined to be outside the basin. | Dairy Remediation | Canceled | 2016 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Adopted
6 | 2112 | SAFE | SRWMD | DEP/ FDACS/ Dairy Producers | SRWMD-04 | Dairy Wastewater Conservation and Nutrient Optimization Project | Improve the management of dairy wastewater by increasing storage pond sizes to achieve greater nutrient uptake and irrigation efficiencies. Six agreements executed to date. Canceled because project location was determined to be outside the basin. | Agricultural BMPs | Canceled | 2014 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | LP6103C | 16/17-119 | N/A | N/A | Adopted
103 | 2103 | SAFE | SRWMD | DEP/ Agricultural Producers/ Local Governments/ Landowners/ Private Companies | SRWMD-05 | Sustainable Suwannee Springs Agriculture Pilot Program - Low Input Agriculture | Operators submit proposals for less intensive cropping, changing the type, or changing fallow or native landscape land use for a certain amount of time or a permanent conservation easement. Load reduction to land estimate of 187,500 lb-N/yr. | Agricultural BMPs | Underway | 2016 | 2026 | 33750 | N/A | Basinwide | N/A | 2500000 | N/A | DEP | $2,500,000 | LP61038 | 17/18-190 | 29.9072 | -82.4723 | Adopted
102 | 2092 | SAFE | SRWMD | DEP/ Agricultural Producers/ Local Governments/ Landowners/ Private Companies | SRWMD-06 | Sustainable Suwannee Springs Agriculture Pilot Program - Advanced Water Quality Improvement Technologies | Agriculture operators, landowners, local governments, private companies, other entities may submit proposals for advanced technologies that can cost-effectively reduce nitrogen in groundwater that contributes to spring flow. | Agricultural BMPs | Underway | 2016 | 2022 | 1832 | N/A | Basinwide | N/A | 190273 | N/A | DEP | $190,273 | LP6103D | 16/17-149 | 29.9072 | -82.4723 | Adopted
| 2104 | SAFE | SRWMD | Agricultural Producers/ Local Governments/ Landowners Private Companies | SRWMD-07 | Regional Initiative Valuing Environmental Resources (RIVER) Program | Cost-share projects for improving wastewater facilities, preventing potential discharge of wastewater into receiving waters, and reducing loads from septic systems. This project was canceled in 2018 because detailed, individual projects were added. | WWTF Upgrade | Canceled | 2012 | N/A | TBD | N/A | Basinwide | N/A | 1500000 | N/A | SRWMD | $1,500,000 | N/A | Not provided | N/A | N/A | Adopted
89 | 2107 | SAFE | SRWMD | Agricultural Producers | SRWMD-08 | Precision Agricultural Practices | Provide cost-share funds to agricultural producers to implement precision nutrient and irrigation management technology. Districtwide program benefits split between Santa Fe and Suwannee BMAPs. Load reduction to land estimate of 312,500 lb-N/yr. | Agricultural BMPs | Underway | 2017 | TBD | 56250 | N/A | Basinwide | N/A | 625000 | N/A | N/A | N/A | LP6103K | Not provided | 29.9072 | -82.4723 | Adopted
132 | 2108 | SAFE | SRWMD | DEP/ Agricultural Producers | SRWMD-09 | Nursery Water Conservation Initiative | Assist nurseries in upgrading from overhead irrigation methods to micro-spray or drip irrigation. To date, 45 nurseries on 300 acres have received assistance. Load reduction to land estimate of 45,000 lb-N/yr. Canceled in 2019. | Agricultural BMPs | Canceled | 2015 | N/A | N/A | N/A | Basinwide | N/A | N/A | N/A | N/A | N/A | S0796 | Not provided | N/A | N/A | Adopted
89 | 4565 | SAFE | SRWMD | DEP/ Agricultural Producers | SRWMD-10 | Precision Ag 2 | Provide cost share funds to agricultural producers within the PFA and BMAP to reduce nutrients and conserve water. | Agricultural BMPs | Underway | 2018 | TBD | TBD | N/A | Basinwide | N/A | 3500 | N/A | DEP/ Producers | DEP - $750,000/ Producers - $250,000 | LP6103K | 17/18-030 | Not provided | Not provided | Adopted
228 | 4566 | SAFE | SRWMD | DEP/ Agricultural Producers | SRWMD-11 | Accelerating Suwannee River Restoration and Silviculture Management | Incentivize silviculture and rural land conservation to reduce groundwater pumping and nitrogen loading in the Middle Suwannee springshed and Ichetucknee River. | Agricultural BMPs | Underway | 2018 | TBD | TBD | N/A | TBD | N/A | TBD | TBD | DEP/ SRWMD | TBD | LP6103G | 19/20-177 | 29.9072 | -82.4723 | Adopted
231 | 4567 | SAFE | SRWMD | City of Lake City | SRWMD-12 | Ichetucknee Springs Quality & Quantity Enhancement | Increase the wetland polishing area from 1 MGD to 3 MGD with estimated recharge of 2 MGD and additional nutrient reduction by adding gravity flow and a recharge well. | Constructed Wetland Treatment | Underway | 2018 | TBD | N/A | N/A | Columbia County | 1 | 1850000 | 40000 | DEP/ City of Lake City | DEP - $1,800,000/ City - $50,000 | LP12031 | N/A | 30.12 | -82.68 | Adopted
206 | 4568 | SAFE | SRWMD | City of Lake City/ Columbia County | SRWMD-13 | Gwen Lake | The project addresses stormwater, flooding, erosion, and sedimentation concerns that impair the water quality and water storage capacity of Gwen Lake and adjacent waterways. | Regional Stormwater Treatment | Underway | 2020 | 2021 | N/A | N/A | Lake City | 800 | 450000 | N/A | SRWMD/ City of Lake City | SRWMD - $200,000/ City - $100,000/ County - $150,000 | N/A | 18/19-202 | 30.1915 | -82.6525 | Adopted
272 | 5460 | SAFE | SRWMD | City of Lake City | SRWMD-14 | Gwen Lake Phase 2 | Installation of a drop structure behind the Parkview Baptist Church stormwater pond, regrade the conveyance, install stabilization to slow the water velocity and reduce the erosion and sedimentation contributing to the infill of Gwen Lake. | Regional Stormwater Treatment | Underway | 2020 | 2021 | TBD | N/A | Columbia County | 111 | 220000 | N/A | SRWMD | SRWMD - $220,000 | N/A | 19/20-124 | 30.1914 | -82.6524 | Adopted
273 | 5472 | SAFE | SRWMD | Gilchrist County | SRWMD-15 | Gilchrist NE 2nd Way Park | Stormwater improvements and bank stabilization. | Shoreline Stabilization | Planned | N/A | 2022 | TBD | N/A | Gilchrist County | N/A | 316444 | 3000 | SRWMD/ FWC | SRWMD - $143,970/ FWC - $167,974/ Gilchrist County - $4,500 | N/A | 19/20-077 | 29.91296 | -82.7743 | Adopted
1738 | 5473 | SAFE | SRWMD | FDOT/ Columbia County | SRWMD-16 | SR 247 Regional Pond (non-FDOT portion) | Construct regional pond to treat runoff on SR 247 and I-75 benefitting Cannon Creek, a tributary to the Santa Fe River. | Regional Stormwater Treatment | Planned | N/A | 2024 | TBD | N/A | Columbia County | 68.6 | 5200000 | 1200 | FDOT/ DEP | TBD | TBD | TBD | 30.1651 | -82.6792 | Adopted
1733 | 5474 | SAFE | SRWMD | DEP | SRWMD-17 | Ft. White Regional Sanitary System | Construct a regional wastewater treatment facility and remove 255 existing septic systems in a phased project. | OSTDS Phase Out | Planned | N/A | 2030 | TBD | N/A | Columbia County | N/A | 11891000 | 92390 | DEP | TBD | N/A | N/A | 29.9167 | -82.7001 | Adopted
296 | 5475 | SAFE | SRWMD | DEP | SRWMD-18 | Lake Butler AWT Upgrade Phases 1-3 | Advanced wastewater treatment facility and created wetland to be constructed in three phases. | WWTF Upgrade | Underway | 2020 | 2025 | 2988 | N/A | Union County | N/A | 23000000 | 400000 | DEP/ Other | DEP - $20,000,000/ Other - $3,000,000 | WS005 | 19/20-055/ 19/20-169 | 29.99 | -82.37 | Adopted
256 | 5797 | SAFE | SRWMD | Alachua Conservation Trust/ DEP | SRWMD-19 | Santa Fe Springs | Land acquisition with conservation easement will ensure less intensive land use. | Land Acquisition | Underway | 2020 | 2021 | N/A | N/A | Columbia County | 254 | 1390381 | TBD | DEP/ Other/ SRWMD | DEP - $617,000/ SRWMD - $139,041/ Other - $634,340 | TBD | TBD | 29.94067 | -82.53107 | Adopted
304 | 5798 | SAFE | SRWMD | DEP/ Municipalities | SRWMD-21 | Wastewater Feasibility Studies | Conduct analysis for using reclaimed water including treatment wetlands. | WWTF Diversion to Reuse | Underway | 2021 | 2023 | TBD | N/A | Basinwide | N/A | 700000 | N/A | DEP | DEP - $700,000 | TBD | TBD | 29.9072 | -82.4723 | Adopted
1739 | 5799 | SAFE | SRWMD | Alachua Conservation Trust/ FWC/ DEP | SRWMD-22 | Devil's Ear | Land acquisition with conservation easement will ensure less intensive land use. | Land Acquisition | Underway | 2020 | 2023 | N/A | N/A | Gilchrist County | 2742 | 8382555 | TBD | DEP/ FWC | DEP - $2,00,000/ Other - $6,382,555 | TBD | TBD | 29.74893 | -82.71736 | Adopted
| 2111 | SAFE | Management Strategies | TBD | WU-01 | Wastewater Treatment Facility Reduction Credits | Achieved by WWTF policy if implemented BMAP-wide, achieving 3 or 6 mg/L. | WWTF Upgrade | Planned | TBD | TBD | 21309 | N/A | Basinwide | TBD | TBD | N/A | TBD | TBD | TBD | Not provided | N/A | N/A | Adopted
232 | 5446 | WACI | DEP | Local Governments | DEP-01 | Greenville Sewer System Phase 1 | Wastewater collection and treatment to phase out approximately 67 septic systems. | OSTDS Phase Out | Underway | Not provided | 2021 | 394 | N/A | Madison County | N/A | 3700000 | N/A | DEP | DEP - $2,700,000/ SRF - $1,000,000 | LP40024 | N/A | 30.466443 | -83.635784 | Adopted
| 5119 | WACI | FDACS | Agricultural Producers | FDACS-01 | BMP Implementation and Verification - Farm Fertilizer | Enrollment and verification of farm fertilizer BMPs by agricultural producers. Acres Treated based on FDACS December 2019 NOI Enrollment and FSAID VI. Reductions based on efficiencies referenced in the BMAP and 100% NOI Enrollment. | Agricultural BMPs | Underway | Not provided | N/A | 51480 | N/A | Basinwide | 11497.6169 | TBD | TBD | FDACS | TBD | N/A | N/A | Not provided | Not provided | Adopted
| 5802 | WACI | FDACS | Agricultural Producers | FDACS-01a | BMP Implementation and Verification - Farm Fertilizer | Enrollment and verification of farm fertilizer BMPs by agricultural producers. Acres Treated and reductions based on FDACS December 2020 NOI Enrollment and FSAID VII. | Agricultural BMPs | Completed | Not provided | 2020 | 27011 | N/A | Basinwide | 25873 | TBD | TBD | Not provided | Not provided | N/A | N/A | Not provided | Not provided | Adopted
| 5120 | WACI | FDACS | Agricultural Producers | FDACS-02 | BMP Implementation and Verification - Livestock Waste | Enrollment and verification of livestock waste BMPs by agricultural producers. Reductions based on efficiencies referenced in the BMAP and 100% NOI enrollment of unenrolled acres. | Agricultural BMPs | Underway | Not provided | N/A | 6843 | N/A | Basinwide | 6368.1356 | TBD | TBD | FDACS | TBD | N/A | N/A | Not provided | Not provided | Adopted
| 5803 | WACI | FDACS | Agricultural Producers | FDACS-02a | BMP Implementation and Verification - Livestock Waste | Enrollment and verification of livestock waste BMPs by agricultural producers. Acres Treated based on FDACS December 2020 NOI Enrollment and FSAID VII. | Agricultural BMPs | Completed | Not provided | 2020 | 3000 | N/A | Basinwide | 10948 | TBD | TBD | Not provided | Not provided | N/A | N/A | Not provided | Not provided | Adopted
| 5129 | WACI | Management Strategies | TBD | GC-01 | Golf Course Reduction Credits | 6 % BMP credit on golf course load to groundwater, assuming 100% BMP implementation by golf course owners. | Fertilizer Reduction | Planned | TBD | TBD | 19 | N/A | Basinwide | TBD | TBD | TBD | TBD | TBD | TBD | 18/19-212 | N/A | N/A | Adopted
| 5127 | WACI | UF-IFAS | Agricultural Producers | IFAS-01 | Winter Forage Demonstration Plots | Established winter forage plots on farms in 2014, 2015, 2016, and 2017 to demonstrate the benefits of overseeding legumes on pastures to reduce dependence on nitrogen for winter forage production. Two field days were held in 2014 and 2016. | Agricultural BMPs | Completed | 2014 | 2017 | N/A | N/A | Jefferson County | Not provided | Not provided | N/A | Not provided | Not provided | N/A | 16/17-248 | Not provided | Not provided | Adopted
| 5128 | WACI | UF-IFAS | Agricultural Producers/ Jefferson County Conservation District | IFAS-02 | Cover Crop Demonstrations | Established cover crop demonstrations on three farms . Demonstrations will reflect cover crops ability to reduce soil erosion, improve water filtration, recycle nutrients, make nitrogen, improve beneficial insect habitat, and improve soil health. | Agricultural BMPs | Underway | Not provided | TBD | TBD | N/A | Jefferson County | 130 | Not provided | N/A | Not provided | Not provided | N/A | 13/14-188 | Not provided | Not provided | Adopted
119 | 5121 | WACI | Jefferson County | SRWMD/ DEP | JC-01 | Wacissa Springs Park Improvement Phase I | Construct picnic shelters, restroom facilities, and boardwalk. | LID- Other | Underway | 2017 | 2018 | TBD | N/A | Jefferson County | TBD | 390126 | TBD | DEP/ County | DEP - $195,063/ Jefferson County - $195,063 | Not provided | Not provided | Not provided | Not provided | Adopted
112 | 5122 | WACI | Jefferson County | SRWMD/ DEP | JC-02 | Wacissa Springs Park Improvement Phase II | Provide slope protection in Wacissa Springs. Remove sediment at Aucilla and Thomas springs. Replace dirt parking lot with asphalt and management facility. TN reduction to land surface of 42,303 lb-N/yr adjusted to reflect load to groundwater. See SRWMD-04. | Shoreline Stabilization | Canceled | 2017 | 2019 | N/A | N/A | Jefferson County | TBD | 521500 | TBD | DEP/ County | DEP - $517,500/ Jefferson County - $4,000 | LP6103E | Not provided | Not provided | Not provided | Adopted
| 5132 | WACI | Management Strategies | TBD | LG-01 | Public Education | Adopted fertilizer ordinance. | Education Efforts | Planned | TBD | TBD | 19 | N/A | Basinwide | TBD | TBD | TBD | TBD | TBD | TBD | N/A | N/A | N/A | Adopted
| 5134 | WACI | Management Strategies | DEP | OSTDS-01 | Enhancement of Existing OSTDS - Voluntary | Upgrade, replacement, modification, addition of effective nitrogen reducing features, initial connection to a central sewer system, or other action to reduce nutrient loading, voluntarily taken by the owner of an OSTDS within the BMAP. | Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Underway | 2018 | N/A | TBD | N/A | Basinwide | N/A | TBD | N/A | DEP | TBD | TBD | N/A | N/A | N/A | Adopted
| 5133 | WACI | Management Strategies | TBD | PD-01 | Dairy BMP Reduction Credits | 15 % BMP credit on dairy load to groundwater assuming 100% owner implemented BMPs on all dairy lands. | Agricultural BMPs | Planned | TBD | TBD | 4642 | N/A | Basinwide | TBD | TBD | TBD | TBD | TBD | TBD | N/A | N/A | N/A | Adopted
| 5130 | WACI | Management Strategies | TBD | SF-01 | Sports Field Reduction Credits | 10 % BMP credit on sports field load to groundwater, assuming 100% BMP implementation by sports field owners. | Fertilizer Reduction | Planned | TBD | TBD | 7 | N/A | Basinwide | TBD | TBD | TBD | TBD | TBD | TBD | 16/17-164 15/16-032 | N/A | N/A | Adopted
106 | 5124 | WACI | SRWMD | DEP/ Local Governments | SRWMD-01 | Coastal Rivers Basin SWIM Plan | Implementation and periodic review and update of the Coastal Rivers SWIM Plan which includes the Aucilla River and Wacissa Spring Group. | Study | Completed | 2015 | 2017 | N/A | N/A | Basinwide | N/A | 100000 | N/A | NFWF | Not provided | N/A | 15/16-052 | 30.4914081 | -83.7858564 | Adopted
| 5125 | WACI | SRWMD | Jefferson County | SRWMD-02 | Lower Aucilla River Hydrographic Survey | Complete digital hydrographic survey that will allow creation of a hydrological model of the Aucilla/Wacissa watershed. | Study | Completed | 2014 | 2014 | N/A | N/A | Jefferson County | N/A | 200000 | N/A | SRWMD | SRWMD - $200,000 | N/A | Not provided | 30.4914081 | -83.7858564 | Adopted
116 | 5126 | WACI | SRWMD | Jefferson County | SRWMD-03 | Walker Springs Road Cross Drains | Improve flood protection and erosion at three unpaved road crossings over Bailey Mill Creek. | Stormwater System Rehabilitation | Completed | 2016 | 2018 | N/A | N/A | Jefferson County | N/A | 139907 | TBD | SRWMD | SRWMD - $39,420/ Jefferson County - $106,987 | N/A | 16/17-192 | 30.3429 | -83.9169 | Adopted
112 | 5447 | WACI | SRWMD | Jefferson County | SRWMD-04 | Wacissa Springs Water Quality Improvement | Slope protection; remove sediment at Aucilla Springs and Thomas Springs; replace dirt parking lot with asphalt and stormwater management facility; install 300 ft. boardwalk. | Shoreline Stabilization | Completed | 2017 | 2019 | N/A | N/A | Jefferson County | N/A | 516698 | N/A | DEP | DEP - $484,698/ Jefferson County - $32,000 | LP6103E | 16/17-248 | 30.340587 | -83.991141 | Adopted
119 | 5448 | WACI | SRWMD | Jefferson County | SRWMD-05 | Wacissa Springs Phase 1 | Bank stabilization to prevent sedimentation and erosion, removal of invasive plants. Water Management Lands Trust Funds/Springs Restoration. One-time sediment removal of 600 cubic yards. | Shoreline Stabilization | Completed | 2015 | 2015 | N/A | N/A | Jefferson County | N/A | 236500 | N/A | WMLTF | WMLTF - $140,000/ Jefferson County - $96,500 | N/A | 13/14-188 | 30.33988 | -83.99148 | Adopted
7 | 5449 | WACI | SRWMD | Local Producers | SRWMD-06 | Dairy Screen Separators | Connect two pivots to the Jeffco Dairy’s wastewater system and retrofit three irrigation systems to low-pressure drop nozzle sprinklers. The project will offset groundwater use with a lower quality water source and allow for better use of nutrients. | Agricultural BMPs | Completed | 2015 | 2020 | TBD | N/A | Jefferson County | N/A | 64460 | N/A | DEP | DEP - $48,345/ Local Producers - $16,115 | S0905 | 18/19-212 | 30.617602 | -83.633248 | Adopted
4 | 5450 | WACI | SRWMD | Local Producers | SRWMD-07 | Fertigation | Fertigating allows the producer to split up the application of fertilizer needed to grow a crop over the entire length of a growing season. | Agricultural BMPs | Completed | 2014 | 2019 | 4115 | N/A | Jefferson County | 381 | 45000 | N/A | DEP/ District | DEP - $25,875/ SRWMD - $7,875/ Local Producers - $11,250 | S0796 | 16/17-164 15/16-032 | 30.617602 | -83.633248 | Adopted
260 | 5451 | WACI | SRWMD | DEP/ Local Governments | SRWMD-08 | Suwannee Valley Springs Initiative | The District is developing a multi-media campaign that will focus on springs awareness and education to increase knowledge, engagement, and passion for water resources among residents and visitors. | Education Efforts | Planned | 2020 | 2022 | N/A | N/A | Basinwide | N/A | 10000 | N/A | DEP | DEP - $300,000 | NF049 | N/A | 30.5028 | -83.7851 | Adopted
89 | 5452 | WACI | SRWMD | Local Producers | SRWMD-09 | Precision Ag | Implementation of soil type mapping, soil and tissue sampling, and aerial imagery to reduce fertilizer and lime application on two farms. | Fertilizer Reduction | Underway | 2017 | 2020 | 3276 | N/A | Madison County | 728 | 24080 | N/A | DEP | DEP - $18,060/ Local Producers - $6,020 | LP6103K | Not provided | 30.4979 | -83.6092 | Adopted
| 5131 | WACI | Management Strategies | TBD | WU-01 | Wastewater Treatment Facility Reduction Credits | Achieved by WWTF policy if implemented BMAP-wide, achieving 3 or 6 mg/L. | WWTF Upgrade | Planned | TBD | TBD | 2026 | N/A | Basinwide | TBD | TBD | TBD | TBD | TBD | TBD | N/A | N/A | N/A | Adopted
53 | 4500 | SUWA | Alliance Dairy | Not provided | AD-01 | Rotational Grazing and Aerobic Digester Pilot Project | Not provided. | BMPs | Underway |  | Not provided | Not provided | N/A | Lower Suwannee River Basin | Not provided |  | Not provided | Not provided | Not provided | N/A |  |  |  | Adopted
| 4485 | SUWA | Town of Branford | DEP/ SRWMD | BRAN-01 | Advanced Wastewater Treatment Facility (WWTF) | Upgrade WWTF from secondary to advanced water treatment. | WWTF Upgrade | Planned |  | TBD | TBD | N/A | Middle Suwannee River Basin | N/A | 1500000 | Not provided | DEP/ SRWMD | TBD | TBD |  |  |  | Adopted
12 | 4484 | SUWA | Town of Branford | SRWMD | BRAN-02 | Branford Wastewater Effluent Pond Failure Repairs | Replace effluent pond at WWTP with tanks. | WWTF Upgrade | Underway | 2018 | 2018 | TBD | N/A | Middle Suwannee River Basin | N/A | 368868 | Not provided | Town/ SRWMD | SRWMD - $231,500 Town - $137,368 | N/A |  |  |  | Adopted
18 | 4483 | SUWA | City of Chiefland | DEP | CH-01 | Biosolids Treatment Unit Replacement | Reconstruct the city's aged biosolids treatment unit (digester). The project includes two new tanks and other equipment to better treat the biosolids. | WWTF Upgrade | Completed | 2018 | 2019 | TBD | N/A | Lower Suwannee River Basin | N/A | 418400 | Not provided | City/ DEP | DEP - $376,560 City - $41,840 | LP61034 |  |  |  | Adopted
74 | 4523 | SUWA | Dixie County | DEP/ SRWMD | DC-01 | Lower Suwannee River Springs Restoration and Aquifer | Restore ~500 acres of sand ponds and rehydrate ~1,250 acres of wetlands by re-establishing N/natural flow through N/natural recharge features and an aquifer recharge well. The project will conserve ~3.26 mgd in water supporting water supply and spring flo | Hydrologic Restoration | Underway |  | 2018 | TBD | N/A | Lower Suwannee River Basin | 1750 | 2406359 | Not provided | County/ DEP/ SRWMD | DEP - $2,200,000 SRWMD - $106,359 County - $100,000 | LP61039 |  |  |  | Adopted
28 | 4520 | SUWA | Dixie County | DEP/ SRWMD | DC-02 | Cow Pond Drainage Basin Aquifer Recharge Project | Re-establish Natural drainage patterns and use natural recharge features and aquifer recharge wells to restore approx. 300 acres of sand ponds and rehydrate approx. 1,750 acres of wetlands while conserving 1.69 MGD of water and support spring flow. | Hydrologic Restoration | Underway |  | 2018 | TBD | N/A | Lower Suwannee River Basin | 2050 | 1600000 | Not provided | County/ DEP/ SRWMD | DEP - $1,500,000 SRWMD - $50,000 County - $50,000 | LP6103B |  |  |  | Adopted
| 4521 | SUWA | FDACS | Agricultural Producers | FDACS-01 | BMPs Implementation and Verification - Farm Fertil | Implementation of existing BMPs on applicable acreage. Up to 15% reduction in load to groundwater. | BMPs | Underway |  | Not provided | 869247 | N/A | Basinwide | 198638 | 10084985 | N/A | FDACS | TBD | N/A |  |  |  | Adopted
| 4522 | SUWA | FDACS | Agricultural Producers | FDACS-02 | BMPs Implementation and Verification - Livestock W | Implementation of existing BMPs at applicable facilities. Up to 10% reduction in load to groundwater. | BMPs | Underway |  | Not provided | 208739 | N/A | Basinwide | 155135 | 7909822 | N/A | FDACS | TBD | N/A |  |  |  | Adopted
| 4528 | SUWA | FDOT District 2 | N/A | FDOT-01 | Fertilizer Elimination | Eliminate fertilizer in rights-of way. | Fertilizer Cessation | Completed |  | Not provided | TBD | N/A | Basinwide | 2898 |  | N/A | Not provided | Not provided | N/A |  |  |  | Adopted
42 | 4529 | SUWA | FDOT Central Office | SRWMD | FDOT-02 | FDOT Water Quality Pilot Project | Comparison of the nutrient removal effectiveness of two different types of biosorptive activated media in a roadside swale just east of Fanning Springs. | Study | Underway |  | 2018 | N/A | N/A | Lower Suwannee River Basin | N/A | 180101 | N/A | SRWMD | 180101 | N/A |  |  |  | Adopted
| 4519 | SUWA | FFB | Suwannee River Partnership | FFB-01 | Agricultural Producer Workshops | Workshops with agricultural producers in the basin. | BMPs | Underway |  | Not provided | TBD | N/A | Basinwide | N/A |  | Not provided | Not provided | Not provided | Not provided |  |  |  | Adopted
| 4515 | SUWA | FFB | Suwannee River Partnership | FFB-02 | County Alliance for Responsible Environmental Stew | Stewardship program active within the basin. | BMPs | Underway |  | Not provided | TBD | N/A | Basinwide | N/A |  | Not provided | Not provided | Not provided | Not provided |  |  |  | Adopted
| 4516 | SUWA | DEP FPS | N/A | FPS-01 | Fanning Springs State Park Restoration | Replant submerged aquatic vegetation (SAV) in spring run of Fanning and Little Fanning Springs. | SAV Planting | Planned |  | TBD | TBD | N/A | Lower Suwannee River Basin | TBD |  | Not provided | DEP | TBD | TBD |  |  |  | Adopted
| 4526 | SUWA | FPS | N/A | FPS-02 | Manatee Spring State Park Restoration | Replant SAV in spring run. | SAV Planting | Planned |  | TBD | TBD | N/A | Lower Suwannee River Basin | TBD |  | Not provided | DEP | TBD | TBD |  |  |  | Adopted
| 4527 | SUWA | FPS | N/A | FPS-03 | Troy Spring State Park Restoration | Shoreline stabilization at spring run. | Shoreline Stabilization | Planned |  | TBD | TBD | N/A | Middle Suwannee River Basin | TBD |  | Not provided | DEP | TBD | TBD |  |  |  | Adopted
39 | 4482 | SUWA | City of Fanning Springs | DEP/ SRWMD | FS-01 | Fanning Springs Water Quality Improvement Project, | Expansion of wastewater collection and transmission system to convert septic to sewer in Areas 1-4 (65 septic systems). | Wastewater Service Area Expansion | Completed | 2015 | 2017 | 1300 | N/A | Lower Suwannee River Basin | N/A | 1276360 | Not provided | City/ DEP/ SRWMD | City - $662,000 DEP - $492,960 SRWMD - $121,440 | S0794 |  |  |  | Adopted
40 | 4481 | SUWA | City of Fanning Springs | DEP/ SRWMD | FS-02 | Fanning Springs Water Quality Improvement Project, | Expansion of wastewater collection and transmission system to convert septic to sewer in Area 10 (60 septic systems). | Wastewater Service Area Expansion | Completed | 2018 | 2020 | 4300 | N/A | Lower Suwannee River Basin | N/A | 2120000 | Not provided | DEP/ SRWMD / City | DEP - $2,000,000 SRWMD - $120,000 | LP61030 |  |  |  | Adopted
41 | 4480 | SUWA | City of Fanning Springs | DEP/ SRWMD | FS-03 | Fanning Springs Water Quality Improvement Project, | Expansion of wastewater collection and transmission system to convert 198 septic systems to sewer in Areas 5-9. | Wastewater Service Area Expansion | Underway |  | 2018 | 4554 | N/A | Lower Suwannee River Basin | N/A | 3395100 | Not provided | City/ DEP/ SRWMD | DEP - $3,355,100 City - $40,000 | LP61036 |  |  |  | Adopted
| 4479 | SUWA | City of Fanning Springs | DEP/ SRWMD | FS-04 | Advanced Wastewater Treatment (AWT) System Expansion | Construction of a new AWT facility that will have capacity for wastewater flows from Lancaster Prison and a portion of Alliance Dairy to benefit Hart and Otter Springs. | WWTF Upgrade | Planned |  | TBD | TBD | N/A | Lower Suwannee River Basin | N/A | 7000000 | Not provided | City/ DEP/ SRWMD | TBD | TBD |  |  |  | Adopted
| 4478 | SUWA | City of Fanning Springs | DEP/ SRWMD | FS-05 | Lancaster Prison/ Alliance Dairy/ City of Fanning | Convey wastewater from Lancaster Prison and Alliance Dairy (both facilities are secondary treatment) to City's advanced WWTF for treatment and recharge wetlands. | Wastewater Service Area Expansion | Planned |  | TBD | TBD | N/A | Lower Suwannee River Basin | N/A | 10000000 | Not provided | City/ DEP/ SRWMD | TBD | TBD |  |  |  | Adopted
85 | 4514 | SUWA | Gilcrhist County | DEP | GC-01 | Hart and Otter Springs Water Quality Improvement P | A three-phase project to decommission septic systems at Otter and Hart Springs and to decommission the wastewater package plant at Hart Springs to connect to Fanning Springs WWTP. | Wastewater Service Area Expansion | Underway |  | 2022 | 1724 | N/A | Lower Suwannee River Basin | N/A | 5979740 | Not provided | DEP | DEP - $1,829,890 (Phase I) | LP61035 |  |  |  | Adopted
| 4473 | SUWA | Golf Courses | TBD | GOLF-01 | Golf Course Reduction Credits | 6% BMP credit on golf course load to groundwater, assuming 100% BMP implementation by golf course owners. | BMPs | Planned |  | TBD | 705 | N/A | Lower Suwannee and Middle Suwannee River Basins |  |  | N/A | TBD | TBD | TBD |  |  |  | Adopted
90 | 4513 | SUWA | Lafayette County | SRWMD | LC-01 | County Road 300 Stormwater Improvement Project | Design and construction of a stormwater collection and conveyance system that will increase stormwater storage. | Stormwater System Upgrade | Underway |  | 2018 | TBD | N/A | Middle Suwannee River Basin | Not provided | 152550 | Not provided | SRWMD / County | SRWMD - $142,550 County - $10,000 | N/A |  |  |  | Adopted
| 4503 | SUWA | Local Governments | TBD | LG-01 | Public Education | Adopted fertilizer ordinance. | Education Efforts | Planned |  | TBD | 1466 | N/A | Basinwide | N/A |  | N/A | TBD | TBD | TBD |  |  |  | Adopted
34 | 4477 | SUWA | City of Live Oak | SRWMD | LO-01 | Stormwater, Drainage, and Aquifer Recharge Well Re | Installation of 60 wells for aquifer recharge. | Groundwater Management | Underway | 2022 | Not provided | TBD | N/A | Middle Suwannee River Basin | Not provided | 7200000 | Not provided | City/ SRWMD | Not provided | Not provided |  |  |  | Adopted
105 | 4476 | SUWA | City of Live Oak | SRWMD | LO-02 | Suwannee Country Club (SCC) Reuse Connection | Connect the SCC golf course to the City of Live Oak reuse line and install a pump station. | BMPs | Completed | 2017 | 2018 | TBD | N/A | Middle Suwannee River Basin | Not provided | 129344 | Not provided | SRWMD | 129344 | N/A |  |  |  | Adopted
9 | 4475 | SUWA | City of Live Oak | SRWMD | LO-03 | Live Oak 49/90 Lift Station Improvements | Install a mixer in the lift station to eliminate sewage spills and improve water quality. | WWTF Upgrade | Completed | 2017 | 2017 | TBD | N/A | Middle Suwannee River Basin | N/A | 15363 | Not provided | City/ SRWMD | SRWMD - $12,690 City - $2,673 | N/A |  |  |  | Adopted
94 | 4474 | SUWA | City of Live Oak | TBD | LO-04 | 9th and Scriven Regional Stormwater Management Fac | Reduce flooding by increasing runoff treatment in stormwater facility. | Stormwater System Upgrade | Underway | 2018 | 2018 | TBD | N/A | Middle Suwannee River Basin | Not provided | 92000 | Not provided | Not provided | Not provided | N/A |  |  |  | Adopted
| 4486 | SUWA | City of Live Oak | DEP/ SRWMD | LO-05 | Stormwater, Drainage, and Aquifer Recharge Well Pr | Identification of a minimum of five existing, high priority stormwater drainage/aquifer drainage wells not within FDOT right of-way to retrofit wells with a pretreatment method that may include: detention/retention, biological nutrient removal, skimmers, | Stormwater System Upgrade | Planned |  | TBD | TBD | N/A | Middle Suwannee River Basin | Not provided | 866800 | Not provided | City/ DEP/ SRWMD | TBD | TBD |  |  |  | Adopted
| 4505 | SUWA | City of Live Oak | DEP/ SRWMD | LO-06 | 2nd St. and Evelyn Ave. Wastewater System Extensio | Extend the City's wastewater collection system to serve approximately 30 homes. | Wastewater Service Area Expansion | Planned |  | 2024 | 1050 | N/A | Middle Suwannee River Basin | N/A | 1089300 | Not provided | City/ DEP/ SRWMD | TBD | TBD |  |  |  | Adopted
80 | 4530 | SUWA | City of Madison | SRWMD | MAD-01 | Lake Frances Sediment Control | This project will improve the quality of stormwater discharged to Lake Frances, which receives most stormwater in the city, a 61-acre watershed. | Stormwater System Upgrade | Underway | 2022 | 2023 | TBD | N/A | Withlacoochee River Basin | 61 | 77525 | Not provided | SRWMD | SRWMD - $42,850 City - $34,675 | N/A |  |  |  | Adopted
75 | 4512 | SUWA | Madison County | DEP/ Nestle Waters/ SRWMD/ City of Madison | MC-01 | Madison Blue Spring Aquifer Recharge | Rehabilitate or replace up to six existing drainage wells to improve aquifer recharge rates. Recharge benefits are estimated up to 3.4 mgd. | Groundwater Management | Underway |  | 2020 | 41850 | N/A | Withlacoochee River Basin | N/A | 2500000 | Not provided | DEP/ Nestle Waters/ County/ SRWMD/ City of Madison | DEP - $2,150,000 Nestle Waters - $225,000 County - $75,000 SRWMD - $50,000 |  |  |  |  | Adopted
| 4507 | SUWA | Various | DEP | OSTDS-01 | Enhancement of Existing OSTDS - Voluntary | Repair, upgrade, replacement, drainfield modification, addition of effective nitrogen reducing features, initial connection to a central sewerage system, or other action to reduce nutrient loading, voluntarily taken by the owner of an OSTDS within the BMA | OSTDS Enhancement | Underway |  | N/A | TBD | N/A | Basinwide | N/A |  | N/A | DEP | TBD | TBD |  |  |  | Adopted
| 4510 | SUWA | Various | DEP | OSTDS-02 | Enhancement of Existing OSTDS - Required | Repair, upgrade, replacement, drainfield modification, addition of effective nitrogen reducing features, initial connection to a central sewerage system, or other action taken to comply with the OSTDS Remediation Plan for the group of systems identified f | OSTDS Enhancement | Planned |  | TBD | TBD | N/A | Inside PFA | N/A |  | N/A | DEP | TBD | TBD |  |  |  | Adopted
| 4506 | SUWA | Permitted Dairies | TBD | PD-01 | Dairy Reduction Credits | 15% BMP credit on dairy load to groundwater assuming 100% owner implemented BMPs on all dairy lands. | BMPs | Planned |  | TBD | 50877 | N/A | Middle Suwannee River Basin | N/A |  | N/A | TBD | TBD | TBD |  |  |  | Adopted
56 | 4511 | SUWA | Suwannee County | DEP/ SRWMD | SC-01 | WWTF at I-75/CR 136 Interchange | Construction of new WWTF at an interchange in proximity to the Suwannee River. 32 commercial septic systems will be converted to the WWTF. | Wastewater Service Area Expansion | Underway |  | Not provided | 39894 | N/A | Middle Suwannee River Basin | N/A | 3330000 | Not provided | DEP / County | DEP - $2,780,000 County - $550,000 |  |  |  |  | Adopted
| 4488 | SUWA | Sports Fields | TBD | SF-01 | Sports Field Reduction Credits | 10% BMP credit on sports field load to groundwater, assuming 100% BMP implementation by sports field owners. | BMPs | Planned |  | TBD | 346 | N/A | Lower Suwannee and Middle Suwannee River Basins |  |  | N/A | TBD | TBD | TBD |  |  |  | Adopted
106 | 4501 | SUWA | SRWMD | DEP/ Local Governments | SRWMD-01 | Suwannee River Surface Water Improvement Managemen | Implementation and periodic review and update of the Suwannee River SWIM Plan. | Study | Underway |  | 2017 | N/A | N/A | Basinwide | N/A | 238563 | Not provided | SRWMD | 238563 | N/A |  |  |  | Adopted
4 | 4518 | SUWA | SRWMD | Agricultural Producers | SRWMD-02 | Advanced Nutrient Management Through Center Pivots | Fertigation system installation and center pivot retrofits. | BMPs | Underway |  | 2022 | 272760 | N/A | Basinwide | Not provided | 1190700 | Not provided | DEP/ SRWMD | DEP - $915,000 SRWMD - $33,150 Producers - $242,500 | S0796 |  |  |  | Adopted
7 | 4508 | SUWA | SRWMD | DEP/ Dairy Producers | SRWMD-03 | Improved Nutrient Application Practices in Dairy Opersations | To date, nine agreements with dairies to install screen separators to reduce wastewater solids. | BMPs | Underway |  | 2022 | 95000 | N/A | Middle Suwannee River Basin | Not provided | 2670000 | Not provided | DEP/ SRWMD | DEP - $2,120,000 SRWMD - $20,000 Producers - $530,000 | S0905 |  |  |  | Adopted
8 | 4499 | SUWA | SRWMD | DEP/ Dairy Producers | SRWMD-04 | Dairy Wastewater System Improvement | Cost-share projects with dairies to invest in advanced treatment technologies (bioreactors), additional wastewater storage, and advanced manure solid separation. | BMPs | Underway |  | 2023 | 10000 | N/A | Middle Suwannee River Basin | Not provided | 1800000 | Not provided | DEP/ SRWMD | DEP - $1,500,000 SRWMD - $300,000 | LP6103C |  |  |  | Adopted
6 | 4502 | SUWA | SRWMD | DEP/ FDACS/ Dairy Producers | SRWMD-05 | Dairy Wastewater Conservation and Nutrient Optimiz | Improve the management of dairy wastewater by increasing storage pond sizes to achieve greater nutrient uptake and irrigation efficiencies. | BMPs | Completed |  | 2020 | 62000 | N/A | Middle Suwannee River Basin | Not provided | 1885590 | Not provided | DEP/ FDACS/ SRWMD/ Producers | DEP - $920,000 FDACS - $250,000 SRWMD - $298,004 Producers - $417,586 | S0796 |  |  |  | Adopted
103 | 4492 | SUWA | SRWMD | DEP/ Agricultural Producers/ Local Governments/ La | SRWMD-06 | Sustainable Suwannee Springs Agriculture Pilot Pro | Agriculture operators are invited to submit proposals to transition to less intensive cropping systems, change the type of cropping system, or change the land use to fallow or native landscape for a certain amount of time or a permanent conservation easem | BMPs | Underway | 2020 | 2024 | 225000 | N/A | Basinwide | Not provided | 3000000 | Not provided | DEP | 3000000 | LP61038 |  |  |  | Adopted
102 | 4493 | SUWA | SRWMD | DEP/ Agricultural Producers/ Local Governments/ La | SRWMD-07 | Sustainable Suwannee Springs Agriculture Pilot Pro | Agriculture operators, landowners, local governments, private companies, other entities may submit proposals for advanced technologies that can cost-effectively reduce nitrogen in groundwater that contributes to spring flow. | BMPs | Underway | 2020 | 2024 | 32700 | N/A | Basinwide | Not provided | 1234626 | Not provided | DEP/ Producers | DEP - $1,000,000 Producers - $234,626 | LP6103D |  |  |  | Adopted
89 | 4494 | SUWA | SRWMD | Agricultural Producers/ Local Governments/ Landown | SRWMD-08 | Regional Initiative Valuing Environmental Resource | Benefits of the annual cost-share projects include: improving wastewater facilities serving hundreds of residents and commercial entities, preventing potential discharge of wastewater into receiving waters during various flood events, and significantly re | WWTF Upgrade | Underway |  | Annual | TBD | N/A | Basinwide | N/A | 1500000 | Not provided | SRWMD | 1500000 | N/A |  |  |  | Adopted
89 | 4495 | SUWA | SRWMD | Agricultural Producers | SRWMD-09 | Precision Agricultural Practices | Provide cost-share funds to agricultural producers within the BMAP area to implement precision nutrient and irrigation management technology. | BMPs | Underway |  | Not provided | TBD | N/A | Basinwide | N/A | 2500000 | Not provided | SRWMD | 2500000 | N/A |  |  |  | Adopted
78 | 4496 | SUWA | SRWMD | DEP/ Dixie County | SRWMD-10 | Middle Suwannee River Springs Restoration and Aquifer | Installation of hydraulic structures in southeast Lafayette and northeast Dixie counties with the objective of restoring natural water drainage patterns. The project will recharge the aquifer with ~ 10 mgd of water over ~ 1,500 acres of ponds and 4,000 ac | Hydrologic Restoration | Underway |  | TBD | TBD | N/A | Middle Suwannee River Basin | 5500 | 1900000 | Not provided | SRWMD/ Dixie County/ DEP | DEP - $1,548,000 SRWMD - $277,000 County - $75,000 | S0675 |  |  |  | Adopted
| 4497 | SUWA | SRWMD | Timber Company | SRWMD-11 | Middle Suwannee River Springs Restoration and Aquifer | Phase II is over 6,000 acres and will rehydrate natural systems along and adjacent to the southeastern margin of Mallory Swamp; thereby increasing available surface water for wetland hydration and groundwater recharge, which will enhance springs restorati | Hydrologic Restoration | Planned |  | TBD | TBD | N/A | Middle Suwannee River Basin | 6000 |  | Not provided | SRWMD/ DEP | TBD | N/A |  |  |  | Adopted
48 | 4498 | SUWA | SRWMD | Gilchrist County | SRWMD-12 | Otter Springs Restoration | Replace or fix deteriorating retaining walls, stabilize the springs banks to control further erosion, and construct access points to the spring and spring run. It is anticipated this project will benefit the spring by removing nutrients, sediments, and de | Shoreline Stabilization | Completed |  | 2018 | Not provided | N/A | Lower Suwannee River Basin | Not provided | 140000 | Not provided | SRWMD | 140000 | N/A |  |  |  | Adopted
48 | 4509 | SUWA | SRWMD | Gilchrist County | SRWMD-13 | Hart Springs Restoration | Improve water quality and spring flows. | Hydrologic Restoration | Completed |  | 2015 | Not provided | N/A | Lower Suwannee River Basin | Not provided | 76500 | Not provided | SRWMD | 76500 | N/A |  |  |  | Adopted
87 | 4524 | SUWA | SRWMD | DEP/ Florida Forest Service | SRWMD-14 | Pot Spring Restoration Project | Stabilize the shoreline along the spring run to prevent sediment from entering the Withlacoochee River. | Shoreline Stabilization | Completed |  | 2020 | 69 | N/A | Middle Suwannee River Basin | Not provided | 183600 | Not provided | DEP | 183600 | LP61033 |  |  |  | Adopted
125 | 4491 | SUWA | SRWMD | Suwannee County | SRWMD-15 | Little River Spring Restoration Project | Stabilize the shoreline along the spring run to prevent sediment from entering the Suwannee River. | Shoreline Stabilization | Completed | 2015 | 2016 | Not provided | N/A | Middle Suwannee River Basin | Not provided | 104587 | Not provided | SRWMD/ Suwannee County | SRWMD - $90,000 County - $14,587 | N/A |  |  |  | Adopted
135 | 4490 | SUWA | SRWMD | Suwannee County | SRWMD-16 | Charles Spring Restoration Project | Improve water quality through the replacement of a failing seawall along the bank of the spring which will reduce sediment loads washing into the spring. | Shoreline Stabilization | Completed | 2015 | 2016 | Not provided | N/A | Middle Suwannee River Basin | Not provided | 112378 | Not provided | County/ SRWMD | SRWMD - $105,000 County - $7,378 | N/A |  |  |  | Adopted
45 | 4489 | SUWA | SRWMD | Dixie County | SRWMD-17 | Gornto Springs Restoration Project | Construct ~300 foot retaining wall, removal of sediment within spring run, and removal of man-made earthen dam and culvert. | Shoreline Stabilization | Completed | 2016 | 2018 | Not provided | N/A | Middle Suwannee River Basin | Not provided | 152985 | Not provided | County/ SRWMD | SRWMD - $145,985 County - $7,000 | N/A |  |  |  | Adopted
121 | 4504 | SUWA | SRWMD | DEP/ Lafayette County | SRWMD-18 | Ravine and Convict Springs Nutrient Capture and Tr | Install interceptor wells to capture high nitrate groundwater. A denitrifying system will be installed at each spring basin that will reduce nutrient loads and return the groundwater at the two locations. | BMPs | Completed |  | 2020 | 4300 | N/A | Middle Suwannee River Basin | Not provided | 630000 | Not provided | DEP/ SRWMD | DEP - $600,000 SRWMD - $30,000 | LP51031 |  |  |  | Adopted
| 4525 | SUWA | City of Trenton | DEP/ SRWMD/ USDA | T-01 | WWTF Improvements | Improvements to City's WWTF to provide advanced wastewater treatment. | WWTF Upgrade | Planned |  | TBD | TBD | N/A | Lower Suwannee River Basin | N/A | 6200000 | Not provided | City/ DEP/ SRWMD/ USDA | TBD | TBD |  |  |  | Adopted
69 | 4517 | SUWA | City of Trenton | SRWMD | T-02 | Trenton Lift Station #7 Rehabilitation | Rehabilitate existing lift station. | WWTF Upgrade | Completed |  | 2017 | Not provided | N/A | Lower Suwannee River Basin | N/A | 207800 | Not provided | City/ SRWMD | SRWMD - $150,000 City - $57,800 | N/A |  |  |  | Adopted
| 4487 | SUWA | Wastewater Utilities | TBD | WU-01 | Wastewater Treatment Facility Reduction Credits | Achieved by WWTF policy if implemented BMAP-wide, achieving 3 or 6 mg/L. | WWTF Upgrade | Planned |  | TBD | 17533 | N/A | Lower Suwannee and Middle Suwannee River Basins | N/A |  | N/A | TBD | TBD | TBD |  |  |  | Adopted